## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Prachi Pundir (23820430)
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
GAMEBOARD
|  | 2 | the game board to be of black color
|  | 3 | the game board to be of particular size
|  | 4 | the game board is not resizeable
|  | 5 | the gameboard to be visible on the screen
|  | 6 | the game to be over if the snake touches border
|  | 7 | the gameboard window to close
SNAKE
|  | 8 | the body colour of the snake to be green and head colour as red
|  | 9 | the snake to move in different direction
|  | 10 | I want the snake to die if it touches itself
|  | 11 | the snake to eat the prey
|  | 12 | the snake to grow
|  | 13 | I want to control the snake movement with the keyboard
PREY
|  | 14 | the location of the prey is set randomly

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Prachi Pundir (23820430)
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form |  | 100%
3.2 |  | Build the game logic
|  |  | Loginform |  | 100%
Authentication
3.2.1 |  |  | Snake logic |  |  | 20%
movement
eating
growing
3.2.2 |  |  | Gameboard logic |  |  | 20%
Visibility
Size
Exit
3.2.3 |  |  | Prey Logic |  |  | 20%
Location
4 | Test and deploy the game |  |  | 3 | 10%
| login form |  |  |  | 100%
5 | Document the game |  |  | 4 | 0%